DEVELOPMENT PROPOSAL

FES “Form Builder”

Field Data Collection System

Accelerated 12-week delivery  •  Development only (UI/UX design excluded)

Prepared by

1.  Executive Summary

FES requires a production-grade, multi-tenant form-builder and field data-collection platform that lets organizations design custom data-collection forms (with rich conditional logic), assign them to programs and field teams, collect data offline in the field, and monitor results through role-based dashboards and analytics.

The provided Figma prototype defines a complete Phase 1 product: 4 user roles, 8 functional modules, and 44+ screens, including a drag-and-drop Form Builder with unlimited-depth conditional follow-up questions and an offline-first mobile field app with sync.

This proposal covers engineering (development) only — UI/UX design is excluded (FES provides the Figma design; we implement to it). It is scoped as an accelerated 12-week delivery by a lean team at India small-company rates.

| Item | Detail |
| --- | --- |
| Timeline | ~12 weeks (≈3 months) |
| Core team | ~6 people (lean, blended) |
| Effort | ~301 person-days |
| Professional fees (ex-GST) | ₹15,29,000 |
| GST @ 18% | ₹2,75,220 |
| Total Payable (incl. GST) | ₹18,04,220 |

The 12-week plan is an accelerated, lean-team delivery. It assumes tight scope prioritization, prompt FES sign-offs, and design delivered per module at sprint start. Detailed cost breakdown in Section 8.

2.  Understanding of Requirements

The prototype is a mid-fidelity wireframe system (no backend, mocked auth, non-persisted data). It clearly specifies what to build. Our job is to build the real, secure product behind it — implementing the front-end from the design FES provides.

2.1  User Roles (4)

FES Super Admin — full platform control: organization CRUD, org approvals, platform-wide user administration, monitoring.

Organization Admin — programs, form builder, indicators, org hierarchy, org users, onboarding wizard.

Program Manager — program oversight, form requests, submission review.

Field User — mobile-first, offline data collection and sync.

2.2  Functional Modules (7)

Authentication & Access —  email/mobile login, OTP verification, session handling, permission control, first-time onboarding.

Organization Management —  list, approve/reject, add/edit, detail, hierarchy tree (Org → Division → Department → Team).

Program Management —  programs CRUD, indicator mapping, assign forms to programs.

Form Management (Form Builder) —  the core: drag-and-drop editor, 11+ field types, field property panel, unlimited-depth conditional follow-up questions, preview, draft/publish.

User & Role Management —  invite flow, user lists, role assignment, RBAC.

Indicator Management —  indicator library, CRUD, categorization, mapping to programs.

Help, Onboarding & Support —  setup wizard, contextual help, help center / FAQs.

Plus supporting areas: dashboards & analytics, submissions review, template gallery, settings, and error / empty states.

2.3  The Two Hardest Pieces (drive most of the estimate)

Form Builder with unlimited nesting — a recursive, path-based schema where any answer can trigger follow-up questions to any depth, each with its own field types and validation. Requires a robust schema model, versioning, and a performant recursive editor UI.

Offline-first field app + sync — local storage of form definitions and responses, photo/GPS capture, background sync, and conflict resolution when connectivity returns.

3.  Proposed Technical Solution

The prototype is already React + TypeScript. We carry that forward and build a matching backend.

Frontend (Web admin): React 18 + TypeScript, Vite, Tailwind, Radix/shadcn UI, React Router, Recharts (reuses the prototype's stack), implemented from FES-provided Figma design.

Backend / API: Node.js (NestJS) or Python (Django REST) — REST/JSON, JWT auth, role-based authorization, multi-tenant data isolation.

Database: PostgreSQL (relational core + JSONB for flexible form schemas & responses).

File / Media storage: S3-compatible object storage (photos, uploads, signatures).

Infra / DevOps: Dockerized services, CI/CD pipeline, staging + production environments, monitoring & backups.

Key engineering components: multi-tenant data model with RBAC; form-schema engine (nested/recursive definitions with versioning & publish); submission engine (validation, media, audit); sync engine (change-log, reconciliation, conflict resolution); OTP / notification services.

4.  Delivery Approach

Methodology: Agile / Scrum, 2-week sprints (6 sprints over 12 weeks), sprint demos to FES.

Environments: Dev → Staging (for FES review / UAT) → Production.

Quality: automated tests on critical logic (form schema, sync), continuous manual QA, and a final hardening / UAT week before launch.

Communication: weekly status, sprint demo every 2 weeks, single point of contact.

5.  Timeline & Phase Plan (12 Weeks)

Delivered in 6 two-week sprints. Backend and frontend run in parallel; QA is continuous.

| Sprint | Weeks | Focus / Deliverables |
| --- | --- | --- |
| Sprint 1 – Foundation | Weeks 1–2 | Discovery & data model, project/CI-CD setup, environments, Auth + OTP + RBAC, app shell & navigation |
| Sprint 2 – Admin & Programs | Weeks 3–4 | FES Admin (orgs CRUD, approvals, hierarchy tree), Org Admin dashboards, programs, indicators, user management |
| Sprint 3 – Form Builder | Weeks 5–7* | Drag-and-drop editor, all field types, unlimited nested conditional logic, field properties, preview, draft/publish |
| Sprint 4 – Field App | Weeks 8–9 | Mobile-first PWA, form renderer with conditional logic, offline capture (photo/GPS), drafts, sync + conflict resolution |
| Sprint 5 – Analytics & Rest | Weeks 10–11 | Dashboards/charts, submissions review, onboarding wizard, settings, help center, notifications |
| Sprint 6 – QA & Launch | Week 12 | End-to-end testing, security & performance checks, UAT support, bug-fixing, deployment, handover/training |

*Sprint 3 spans ~3 weeks as the Form Builder is the largest component; other sprints are 2 weeks.

6.  Resources Required (Team)

Lean small-company team for a 12-week delivery. Some roles are part-time.

| Role | Count | Allocation | Responsibility |
| --- | --- | --- | --- |
| Frontend Developers (React/PWA) | 2 | Full 12 weeks | Web admin + field PWA + form builder UI |
| Backend Developers (Node/Django + PG) | 2 | Full 12 weeks | APIs, schema engine, sync, auth, multi-tenancy |
| QA Engineer | 1 | ~8 weeks (part) | Test plans, manual + automated testing, UAT |
| Project Manager / Business Analyst | 1 | Part-time | Delivery, backlog, FES liaison, requirements |
| Tech Lead / Architect | 1 | Part-time | Architecture, code review, technical governance |
| DevOps | 0.5 | Part-time | CI/CD, environments, deployment, monitoring |
| Total | ~6 | (shared/part-time) | — |

Client-side (FES) involvement needed: a product owner for fast sign-offs, the final UI design (Figma) and assets, subject-matter input on forms/indicators, UAT testers, and access to third-party services (SMS/email/OTP provider, domains, cloud account).

7.  Effort Estimate (indicative, person-days — development only)

| Work area | Frontend | Backend | QA | Total |
| --- | --- | --- | --- | --- |
| Setup, infra, CI/CD, Auth + OTP + RBAC | 12 | 18 | 4 | 34 |
| Org, program, indicator & user management (admin) | 22 | 20 | 6 | 48 |
| Form Builder (drag-drop + unlimited nesting) | 34 | 16 | 8 | 58 |
| Field app: renderer + offline + sync | 24 | 22 | 8 | 54 |
| Dashboards, analytics & submissions | 12 | 10 | 5 | 27 |
| Onboarding, settings, help, notifications, templates | 8 | 7 | 3 | 18 |
| Error states, polish, integration, hardening, UAT | 3 | 2 | 4 | 9 |
| Subtotal (person-days) | 115 | 95 | 38 | 248 |
| PM / Tech Lead / DevOps (28 + 14 + 11) |  |  |  | 53 |
| Grand total |  |  |  | ~301 |

Fit within 12 weeks: Over ~12 weeks (≈60 working days per person), the team provides roughly 2 × 60 = 120 frontend and 120 backend person-days, plus part-time QA (~40 PD), PM, Tech Lead and DevOps capacity. The ~301 person-days above fit within this capacity and are delivered across the 6 sprints in Section 5.

| Discipline | Required (PD) | Available over 12 wks (PD) | Team |
| --- | --- | --- | --- |
| Frontend | 115 | ~120 | 2 devs × 12 wks |
| Backend | 95 | ~120 | 2 devs × 12 wks |
| QA | 38 | ~40 | 1 × ~8 wks (part-time) |
| PM / Tech Lead / DevOps | 53 | ~55 | shared, part-time |

8.  Budget

Development only (UI/UX design excluded). All amounts in INR at India small-company day-rates. Costs are built up from effort (person-days) × discipline day-rate. GST @ 18% is applied on professional fees.

| # | Cost Component | Effort (PD) | Rate (₹/day) | Amount (₹) |
| --- | --- | --- | --- | --- |
| 1 | Frontend Development (web admin + field PWA + form builder UI) | 115 | 5,000 | 5,75,000 |
| 2 | Backend Development (APIs, schema engine, sync, auth, multi-tenancy) | 95 | 5,500 | 5,22,500 |
| 3 | QA & Testing (test plans, manual + automated, UAT) | 38 | 3,500 | 1,33,000 |
| 4 | Project Management / Business Analysis | 28 | 5,000 | 1,40,000 |
| 5 | Solution Architecture / Tech Lead | 14 | 7,000 | 98,000 |
| 6 | DevOps & Infrastructure (CI/CD, environments, deployment) | 11 | 5,500 | 60,500 |
|  | Subtotal — Professional Fees | 301 |  | 15,29,000 |
|  | GST @ 18% |  |  | 2,75,220 |
|  | Total Payable (incl. GST) |  |  | 18,04,220 |

Rates are indicative India small-company day-rates and may be adjusted based on the final team seniority mix and engagement model.

Recurring / Operational Costs (not included above)

| Item | Indicative |
| --- | --- |
| Cloud infrastructure (staging + prod, storage, DB, backups) | ₹20,000–45,000 / month (scales with usage) |
| SMS/OTP + email provider | Usage-based (₹0.15–0.25 per SMS typical) |
| Post-launch support & maintenance | AMC at ~15–18% of build cost / year |

Third-party costs (cloud, SMS, email, domains, app-store fees) are billed at actuals or paid directly by FES. Recurring costs are exclusive of GST.

Suggested Payment Milestones

| Milestone | % | Trigger |
| --- | --- | --- |
| Mobilization | 20% | Contract signing / kickoff |
| Auth + Admin modules | 20% | Sprints 1–2 accepted (end Week 4) |
| Form Builder | 25% | Sprint 3 accepted (end Week 7) |
| Field App (offline + sync) | 20% | Sprint 4 accepted (end Week 9) |
| Analytics & remaining modules | 10% | Sprint 5 accepted (end Week 11) |
| Go-live & handover | 5% | UAT sign-off & production launch (Week 12) |

Each milestone percentage is applied to the total contract value; GST @ 18% is added to every invoice.

9.  Assumptions

The 12-week timeline is aggressive and assumes tight scope prioritization, prompt FES sign-offs (within 1–2 business days), and no major mid-sprint scope changes; lower-priority items may be phased if needed to protect the launch date.

The Figma prototype is the agreed functional scope; material additions are handled via change requests.

Field app is delivered as an installable PWA; native iOS/Android apps are an optional add-on.

One environment set (dev/staging/prod) on a cloud account provided/approved by FES.

English-language UI initially; multi-language / localization can be added (estimate on request).

10.  Key Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Aggressive 12-week timeline | Strict sprint scope, parallel FE/BE tracks, lower-priority items phased; weekly burn-down tracking |
| Design delivered late/incomplete by FES | Back-end/API work proceeds in parallel; design needed per module at sprint start |
| Form-builder nesting complexity | Prototyped in Sprint 3 first; schema model validated in Sprint 1 |
| Offline sync edge cases / conflicts | Clear conflict-resolution strategy defined up front; dedicated test pass |
| Scope creep | Change-request process; backlog locked per sprint |

11.  Deliverables

Production web application (all admin roles) + field PWA, implemented from FES design.

Backend APIs, database, and infrastructure (CI/CD).

Source code, technical documentation, and API docs.

Test artifacts and UAT support.

Deployment to production + admin/user handover training.

12.  Next Steps

Confirm scope and approve this proposal.

Short kickoff to lock data model, sprint plan, and design-handoff schedule.

Sign engagement and mobilize the team.

This is an indicative, development-only proposal (UI/UX design excluded) based on the Phase 1 prototype, scoped for an accelerated 12-week delivery at India small-company rates. Final scope and pricing are confirmed at kickoff.